## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration (days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Initiation
Development of the Project Charter |  |  |  | 2 | bar: WEEK 1 M to WEEK 1 T
Determination of the composition of interest bathrooms |  |  |  | 2 | bar: WEEK 1 W to WEEK 1 R
Formation of the project team |  |  |  | 2 | bar: WEEK 1 F to WEEK 2 M
Milestone: Kick-off
Milestone: Planning
Definition of content |  |  |  | 2 | bar: WEEK 2 W to WEEK 2 R
Definition of works/operations |  |  |  | 2 | bar: WEEK 2 F to WEEK 3 M
Project Resource Estimation |  |  |  | 2 | bar: WEEK 3 T to WEEK 3 W
Determination of the organizational structure of the project |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Definition of successor work |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Job duration estimation |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Schedule Development |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Milestone: Cost estimate |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Budgeting |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Risk identification |  |  |  | 2 | bar: WEEK 4 M to WEEK 4 T
Risk assessment |  |  |  | 2 | bar: WEEK 4 M to WEEK 4 T
Quality planning |  |  |  | 2 | bar: WEEK 4 M to WEEK 4 T
Procurement planning |  |  |  | 2 | bar: WEEK 4 M to WEEK 4 T
Communication planning |  |  |  | 2 | bar: WEEK 4 M to WEEK 4 T
Milestone: Approve project documentation
Milestone: Execution
Selecting Tablet Vendors |  |  |  | 10 | bar: WEEK 4 W to WEEK 6 T
Connecting tablets |  |  |  | 10 | bar: WEEK 4 F to WEEK 6 R
Training employees to work on tablets |  |  |  | 10 | bar: WEEK 5 M to WEEK 6 F
Testing work on tablets |  |  |  | 15 | bar: WEEK 5 T to WEEK 8 M
Test Analysis |  |  |  | 10 | bar: WEEK 8 T to WEEK 10 M
Full-fledged tablet launcher |  |  |  | 10 | bar: WEEK 9 W to WEEK 11 T
Milestone: Test run of new system, with friends and family |  |  |  | 10 | bar: WEEK 11 M to WEEK 12 F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Initiation
Development of the Project Charter |  | 1 | 1 | 2 | 3 | H
Determination of the composition of interest bathrooms |  | 1 | 1 | 2 | 3 | H
Formation of the project team |  | 1 | 1 | 2 | 3 | H
Milestone: Kick-off
Milestone: Planning
Definition of content |  | 1 | 1 | 2 | 3 | M
Definition of works/operations |  | 1 | 1 | 2 | 3 | M
Project Resource Estimation |  | 1 | 1 | 2 | 3 | M
Determination of the organizational structure of the project |  | 1 | 1 | 2 | 3 | H
Definition of successor work |  | 1 | 1 | 2 | 3 | H
Job duration estimation |  | 1 | 1 | 2 | 3 | H
Schedule Development |  | 1 | 1 | 2 | 3 | H
Cost estimate |  | 1 | 1 | 2 | 3 | M
Budgeting |  | 1 | 1 | 2 | 3 | M
Risk identification |  | 1 | 1 | 2 | 3 | L
Risk assessment |  | 1 | 1 | 2 | 3 | H
Quality planning |  | 1 | 1 | 2 | 3 | H
Procurement planning |  | 1 | 1 | 2 | 3 | H
Communication planning |  | 1 | 1 | 2 | 3 | H
Milestone: Approve project documentation
Milestone: Execution
Selecting Tablet Vendors |  | 5 | 5 | 10 | 15 | H
Connecting tablets |  | 5 | 5 | 10 | 15 | H
Training employees to work on tablets |  | 5 | 5 | 10 | 15 | H
Testing work on tablets |  | 10 | 10 | 15 | 20 | H
Test Analysis |  | 5 | 5 | 10 | 15 | M
Full-fledged tablet launcher |  | 5 | 5 | 10 | 15 | M
Milestone: have test run of new system, with friends and family |  | 5 | 5 | 10 | 15 | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Tabletop tech speeds up service and boosts profits, study says | https://www.restaurantdive.com/news/tabletop-tech-speeds-up-service-and-boosts-profits-study-says/560152/ | 2023-07-03
Retail and Restaurant Tablet POS: Everything You Need to Know | https://www.nccusa.com/retail-and-restaurant-tablet-pos-everything-you-need-to-know/ | 2023-07-04
Restaurant tablet ordering system | https://www.upmenu.com/software-for-restaurants/mobile-app-for-restaurant/tablet/ | 2023-07-04

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Faster, more efficient experience | Lobby wait time under 10 min | are customers receiving the correct orders? | 98% of order accuracy | FALSE
Faster, more efficient experience | Сheckout time of 1 minute or less | Have we improved customer satisfaction? | Waitstaff can log into their tablet accounts on the first try | FALSE
Faster, more efficient experience | Reducing the average table turn time by 30 minutes | Are the tablets functioning properly? | Tablet error logs report a maximum of one error per shift | FALSE
Customer satisfaction | 98% of order accuracy | Are customers having a better dining experience with the tablets? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | FALSE
Easy-to-use |  | How quickly are the customers learning how to navigate the tablets? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | FALSE
Easy-to-use | Increase customer retention in tablet areas by 5% | Do all tablets work as expected? |  | FALSE
|  | To what extend the tablets increase work performance? | How much side work the staff are able to complete during the shift | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Lobby wait time under 10 min | are customers receiving the correct orders? | 98% of order accuracy | Have you ever visited S&S restaurants in the past? | Yes/No | Yes | No
Сheckout time of 1 minute or less | Have we improved customer satisfaction? | Waitstaff can log into their tablet accounts on the first try | If you used the tablet, how was your overall experience? | Multiple choice | Very good | Good | Neither good nor bad | Bad | Very bad
Reducing the average table turn time by 30 minutes | Are the tablets functioning properly? Do all tablets work as expected? | Tablet error logs report a maximum of one error per shift | If you used the tablet, how would you consider the experience in terms of navigation, functionality, technical issues, etc? | Multiple choice | Very Satisfying | Somewhat Satisfying | Neither Satisfying nor dissatisfying | Somewhat dissatisfying | Very dissatisfying
98% of order accuracy | Are customers having a better dining experience with the tablets? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | On a scale of 1-5, 1 very little and 5 very long, how long was your wait time? | Scaled | Very little | Little | Neither little nor long | long | very long
Increase customer retention in tablet areas by 5% | How quickly are the customers learning how to navigate the tablets? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | On a scale of 1-5, 1 30 min and 5 2h+, how much time did you spend at the tables? | Scaled | 30 min | 1h | 1h and 30min | 2h | 2h+
| To what extend the tablets increase work performance? | How much side work the staff are able to complete during the shift | Were your orders accutate? | Yes/No | Yes | No
|  |  | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate your overall experience? | Scaled | needs improvements | needs small improvements | fine | good | excellent
|  |  | "The serice was fast and I didn't have to wait more than 15min between two courses" | True/False | TRUE | FALSE
|  |  | "It took me less than 1 min to proceed with the checkout" | True/False | TRUE | FALSE
|  |  | Which was for you the best "pro" in ordering by a tablet? And why? | Open-ended | Open-ended