## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | 82% of guests ordered appetizers and all guests ordered dinner, showing high engagement with the tablets for ordering. | Appetizers — 41 — 82% Dinner — 50 — 100%
Customers | Went well | 40% of guests rated their tablet experience as a 4 out of 5, and 32% rated it as a 5 out of 5, showing that most guests had a positive experience. | 4 — 20 — 40% 5 — Great — 16 — 32%
Customers | Went well | 78% of guests signed up for the newsletter on the tablet, showing high interest in the restaurant. | Yes — 39 — 78%
Customers | Needs improvement | 48% of guests found it difficult to order directly from the menu on the tablet, showing that the interface needs improvement. | 1 — Difficult — 48% | Provide additional training for waitstaff on how to instruct guests on using the tablets. This can improve the experience and ease of use for more guests.
Customers | Needs improvement | 54% of guests waited over 15 minutes for a table and 12-56% waited over 20 minutes for their food, showing that service time needs to be improved. | 15+ min. — 27 — 54% | Analyze the kitchen operations and order process to determine how to reduce wait times. This could include hiring additional staff, improving the layout and workflow, and addressing any technology issues. Implement changes to improve speed and accuracy.
Customers | Needs improvement | 28% of guests reported issues with their order being prepared incorrectly, showing a need to improve kitchen operations and order accuracy. | No — 14 — 28% | Review the tablet interface and menu to determine how the layout and options can be improved to make ordering more intuitive for guests. Solicit additional feedback from guests on their challenges and make changes accordingly.
Project team | Went well | Tablet installation and payments were successful at both locations.
Project team | Went well | Customer satisfaction standards were largely met according to survey results.
Project team | Went well | Technical issues were addressed quickly to minimize disruption.
Project team | Needs improvement | Table turn time did not decrease as much as hoped. More analysis is needed. |  | Table turn time too slow. Analyze and fix, e.g. streamline food/payment, add staff
Project team | Needs improvement | Some food orders were still being sent back, indicating issues with order accuracy. |  | Some food sent back, indicating order errors. Review orders/returns, retrain staff, clarify menu, double check, add photos
Project team | Needs improvement | Internal operational issues impacted task completion, highlighting the need for better planning based on location history and staff availability. |  | Internal issues impacted work. Review locations' needs/staff/challenges. Make location plans, monitor/adjust